## Sheet1
# | Task Name | Duration | Start | ETA | October |  |  |  | November |  |  |  | December
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Set up provided model | 1 week | 2021-10-01 | 2021-10-10 | bar: October 1
2 | Conduct and write up literature review | 2 weeks | 2021-10-01 | 2021-10-17 | bar: October 1 to October 2
3 | Build first N-back model | 3 weeks | 2021-10-11 | 2021-11-07 | bar: October 3 to November 5
4 | Write methodology section | 1 week | 2021-11-01 | 2021-11-07 | bar: November 5
5 | Compare to behavioural data | 1 week | 2021-11-08 | 2021-11-14 | bar: November 6
6 | Build second N-back model | 3 weeks | 2021-11-15 | 2021-12-05 | bar: November 7 to December 9
7 | Compare to behavioural data | 1 week | 2021-11-29 | 2021-12-05 | bar: December 9
8 | Write results section + discussion | 1 week | 2021-12-06 | 2021-12-12 | bar: December 10
9 | Finalize model and report + write reflection | 3 weeks | 2021-12-13 | 2022-01-02 | bar: December 11 to December 12